Quarterly Commitment Summary

# ✅ Commitment

Facilitate a Roundtable series with senior field leaders to improve alignment, surface operational issues, and strengthen leadership bench depth.

# 📊 SMART Breakdown

Specific: Facilitate a Roundtable series with senior field leaders

Measurable: Post-session feedback scores average 8/10 or higher

Achievable: Chance will lead and has capacity to deliver a world-class experience

Relevant: Strengthens continuity, alignment, issue visibility, and field culture

Time-bound: Fully completed by September 10, 2025

# 📍 Milestone Roadmap

1. Design Session Framework – by August 2  
    - Finalize format, topics, and objectives for each session  
    - Identify and confirm 6–8 key senior field leaders to participate  
    - Success = Clear session plan and invites sent
2. Conduct Roundtable #1 – by August 9  
    - Facilitate first session  
    - Capture key takeaways and feedback  
    - Success = Completed session + feedback average ≥ 8/10
3. Conduct Roundtable #2 – by August 23  
    - Build on insights from Roundtable #1  
    - Identify emerging patterns or leadership gaps  
    - Success = Completed session + updated notes and participation log
4. Final Roundtable + Summary Report – by September 10  
    - Complete third session  
    - Deliver concise summary report with aligned priorities, leadership gaps, and next steps  
    - Success = Final session completed + report delivered to leadership

# 👤 Owner

Chance Aguirre

# 📈 Weekly Metrics

* Number of Roundtable Sessions Scheduled
* Percentage of Confirmed Senior Leaders Committed to Attend
* Session Materials or Agenda Prepared (Yes/No)
* Post-Session Feedback Score
* Number of Key Issues or Leadership Gaps Documented